| AI Co-pilot for CIB Incident Support POC Initiative ¦ Leadership Briefing ¦ Q1 2026 | STATUS DESIGN COMPLETE Build Phase Starting |
| --- | --- |

THE PROBLEM WE ARE SOLVING

| Today's Manual Process - Customer email triggers a Jira ticket - L1 engineer manually checks Splunk, OCP health, and recent Prod changes - If unresolved, App Dev team is paged — repeating the same checks - Average triage time: 30–45 minutes per P1/P2 incident - High rate of unnecessary App Dev escalations | With the AI Co-pilot - Jira ticket auto-triggers the AI agent asynchronously - Agent queries Splunk, OCP, and Prod Changes in parallel - Structured triage summary posted to Jira within 30 seconds - Confidence-scored escalation recommendation reduces unnecessary pages - L1 and App Dev both get what they need, instantly |
| --- | --- |

TARGET OUTCOMES FOR POC

| < 30s Triage Time Target | ↓ 60% Unnecessary Escalations | 3 Tools Splunk · OCP · Prod | 100% Audit Trail Coverage | 2–4 wks POC Timeline |
| --- | --- | --- | --- | --- |

HOW IT WORKS — THE ARCHITECTURE IN PLAIN ENGLISH

| 01 | Jira webhook fires when a P1 or P2 incident ticket is created | Trigger |
| --- | --- | --- |
| 02 | Agent receives a sanitised event envelope — no PII leaves the secure gateway | Security |
| 03 | Three tool queries fire simultaneously: Splunk logs, OCP health, last Prod change | Intelligence |
| 04 | Agent compares current state vs 24-hour baseline to detect anomalies | Analysis |
| 05 | LLM synthesises findings into a structured triage summary with confidence score | Synthesis |
| 06 | If confidence is below configurable threshold, escalation is flagged automatically | Decision |
| 07 | Full report posted as a Jira comment; Slack notification fires with priority-based format | Output |

| PARALLEL WORKSTREAMS #; Stream; Owner / Dependency. 1; Platform; Tachyon integration, service accounts, read-only access to Splunk, OCP, Jira; Platform Team. 2; Agent Build; ADK orchestration, MCP tool schemas, stub library, synthesis prompt; Your Team. 3; Output & Demo; Jira comment format, Slack notification, demo scenario script; Your Team. | KEY RISKS & MITIGATIONS Risk; Mitigation; Status. Tachyon not ready in 2–4 weeks; Build against stub layer now; swap Tachyon in post-POC; MANAGED. LLM output inconsistency; Structured prompt templates with versioning; slot-filling not free-form; MANAGED. Confidence threshold too aggressive; Configurable value — tunable during demo without code changes; WATCH. Platform team dependency delay; Raise Tachyon request immediately; stubs unblock build in parallel; WATCH. |
| --- | --- |

| Immediate Actions Required ① Raise Tachyon onboarding request with Platform Team this week ② Confirm escalation threshold owner (business stakeholder, not engineering) ③ Select two demo incident scenarios for stub library design | POC SCOPE: READ-ONLY No PII leaves Tachyon boundary Full audit trail on every agent run Compliant by design |
| --- | --- |